## Sheet1
Week | Date |  | Development Plan | QA
5 | February | 10 | -Research - Database - Map API - Andoid Studio - Git | N/A
6 |  | 17 | - Start Up Pages - Prompt user start up settings - User Accounts - Gmail authentication - Custos Account | - User MUST be able to create an account - User MUST be able to interact w/ first log in UX - User MUST be able to change username
7 |  | 24 | - Home Page - Map SDK (UX/UI) - NavBar (UX/UI) - CautionZone Button (UX/UI) - Search Bar (UX/UI) - Notication (UX/UI) - Event Info (UX/UI) - Database Infrastructure I | - User MUST be able to interact with NavBar - User MUST be able to view map - User MUST be able to click on CautionZone button - User MUST be able to see event info - User MUST be able to type in search bar - User MUST be able to click on Notification button
8 | March | 2 | - Contacts - Contact List (UX/UI) - Add Contact - Remove Contact - Database Infrastructure II | - User MUST be able to add a contact - User MUST be able to remove any contact - User MUST NOT be able to create duplicate contacts - User MUST be able to view their contact list - User MUST be able to share their contact list with others
|  | 9 | - Events - Create Event (UX) - Modify Event (UX) - Invite To Event (UX) - View Events (UX) - Location - Location Object Implementation | - User MUST be able to view create event page - User MUST be able to view modify event page - User MUST be able to view invite contacts page - User MUST be able to view all events - User MUST be able to view current location - User MUST be able to shared/view contact's location
9 |  | 16 | - Events - Create Event (Backend) - Modify Event (Backend) - Invite To Event (Backend) - View Events (Backend) - Contacts II - Event contact communication | - User MUST be able to create normal event and safety event - User MUST be able to modify created event - User MUST be able to invite contacts to event - User MUST be able to events that are created - User MUST NOT be able to modify event they not own - User MUST NOT be able to invite same contact twice - User MUST NOT be able to create event if not passing validation fields
10 |  | 23 | - Caution Zone - Caution Zone form - Caution zone map implementation - Caution Zone expiration structure - Report | - User MUST be able to add a safety pin - User MUST be able to create a caution zone - User MUST be able to set their home location - User MUST NOT be able to see expired caution zone - User MUST be able to see caution zone - User MUST be able to add caution zone within restricted radius
11 |  | 30 | - Emergency System - Set up Emergency contact - Set up safety pin - Notification System | - User MUST be able to alert their emergency contacts - User MUST be able to setup safety pin - User MUST be able to setup emergency contact - User MUST be able to receive notifications from other users
12 | April | 6 | - Web app implementation - Github pages set up - Connect with existing services
13 |  | 13
14 |  | 20
15 |  | 27 | - Promotional Website
Final | May | 4

## Sheet2
| February |  |  | March |  |  |  |  | April
| 10 | 17 | 24 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
Research
Start Up Pages
User Accounts
Home Page
Database Infrastructure
Contacts
Location
Events
Caution Zone
Reports
Emergency System
Notication System
Web App
Promotional Website